## Page1of2
CONSTRUCTION CHANGE ORDER (CO)
[INSTRUCTIONS TO COMPLETE THIS FORM ARE IN RED-COLORED ITALICS AND BRACKETS. COMPLETE EVERY FIELD AND DELETE RED-COLORED TEXT, INCLUDING BRACKETS. GRAY HIGHLIGHTED FIELDS ARE AUTO POPULATED BY FORMULAS.]
CONTRACT NUMBER: |  | [Insert contract PO number] |  |  |  | CHANGE ORDER NUMBER: |  | [Insert CO #]
PROJECT NAME: |  | [Insert Project Name] |  |  |  |  | DATE: | [Insert date]
LOCATION: |  | [Insert Project Address]
CONTRACTOR:
CONTRACTOR ADDRESS:
Contract Number [Insert contract PO number] is hereby amended as follows, and the following Work is authorized in accordance with the Contract Documents and referenced Modifications when this Change Order is properly signed by the Architect, Contractor and Owner (hereinafter “Minnesota State”) and funds are encumbered by Minnesota State: (Cost breakdowns are required per General Conditions of the Contract for Construction.)
WHEREAS, Minnesota State has an Agreement with the Contractor, to provide [Provide a brief description of the Scope of the Work provided under the original Construction]; and
[Insert description, for example, It was necessary to also renovate the restrooms per Building Code Official.]
WHEREAS, it is necessary to modify the original agreement to include the following changes per Proposal Requests (PRs) and
Construction Change Directives (CCDs):
Reference [Insert PR or CCD] | Description [Insert brief description of change] |  |  | Reason |  |  |  | Total
[Insert amount in appropriate column below]
|  |  |  | Error or Ommission | Field Condition | Owner Directive | Regulatory Change
CCD #1 | Add hardware set #4 |  |  | 788 |  |  |  | 788
CCD #2 | Relocate pipe |  |  |  | 1100 |  |  | 1100
PR #5 | Modify door frame |  |  |  | 492 |  |  | 492
CCD #4 | Replace soil at excavated pipe |  |  |  |  | 7106 |  | 7106
CCD#19 | Install exit panic hardware | [5 empty] | 4400 | 4400
CCD#3 | Provide Credit for substrate |  |  |  | -1250 |  |  | -1250
PR #6 | Provide Credit to not remove light |  |  |  |  | -800 |  | -800
| Subtotal |  |  | 788 | 342 | 6306 | 4400
[5 empty] | TOTAL ADDITIONS: |  |  | 11836
THEREFORE, it is agreed that the Contractor shall provide materials and labor as required to install the items listed in the PRs and CCDs above and the Owner shall pay Contractor the sum of:
[Insert description: INCREASE, DECREASE, or NO CHANGE]
INCREASE | of | 11836 | as payment in full for the Work described and in accordance with the attached
breakdown.
[Insert description: INCREASED by X days to new date, DECREASED by x days to new date, or NO CHANGE of existing date]
Substantial completion date shall be |  |  | INCREASED | by | 3 | calendar days to |  | September 29, 2020
[Insert revised date(s) mm/dd/yy of Substantial Completion for each phase, if applicable.]
NO OTHER TERMS OF THE AGREEMENT WILL CHANGE AS A RESULT OF THIS CHANGE ORDER.
This Change Order does not include changes in the Contract Sum, Contract Time or Guaranteed Maximum Price which have been authorized by Construction Change Directive until the cost and time have been agreed upon by both the Owner and Contractor, in which case a Change Order is executed to supersede the Construction Change Directive. All information and signatures on page 2 must be fully completed. Full justification for the requested changes must be included on or attached to this form.
CONTRACT SUMMARY:
1. | The original Contract Sum was | [6 empty] | [Insert amount]
2. | Peviously authorized Change Order additions to date (C.O. Nos.: ________): | [6 empty] | [Insert amount]
3. | Previosly authorized Change Order deductions to date (C.O. Nos.:__________): | [6 empty] | [Insert amount]
4. | The Contract Sum Prior to this Change Order was | [6 empty] | [Insert amount]
5. | The Contract Sum will |  | INCREASE |  | by this Change Order in the amount of |  |  | 11836
6. | The new Contract Sum including this Change Order will be | [6 empty] | #VALUE!
7. | The Substainal Completion Date shall be |  |  |  | INCREASED | by | 3 | days.
The date(s) of Substantial Completion as of the date of this Change Order therefore shall be | [7 empty] | September 29, 2020
IN WITNESS WHEREOF Minnesota State and CONTRACTOR have signed this CONTRACT AMENDMENT,
intending to be bound thereby.
SIGNATURES OF APPROVAL:
1. | ARCHITECT (authorized signature and printed name)
[INSERT NAME OF ARCHITECTURAL FIRM]
Date
Title
2. | CONTRACTOR (authorized signature and printed name)
[INSERT NAME OF CONTRACTOR]
Date
Title
3. | MINNESOTA STATE (authorized signature and printed name)
[INSERT NAME OF COLLEGE OR UNIVERSITY]
Date
Title
4. | AS TO FORM AND EXECUTION (authorized signature and printed name)
Date
Title